## Sheet1
| time | System engineer | Mechanical | Control guy | Electrical | CAD licence | VirtualLab Motion | AMESim | Excel | Simulink | SysML tool
Concept Design | 1 w | x | [8 empty] | x
Create Mech | several days |  | x |  |  | x
Create MBM | one day |  | x |  |  |  | x
Create electical model | several days |  |  |  | x |  |  | x
Select Battery | several hours |  | x |  | x |  |  |  | x
Select Motor | several hours |  | x |  | x |  |  |  | x
Adapt Mechanical | start: 1 day... |  | x |  |  | x
Process Mech Design | 1 hour |  |  |  |  | x | [5 empty] | Cost per time
Adapt MBM | start: 0.5 day... |  | x |  |  |  | x |  |  |  |  | Cost unit
Design PID | start: 1 day... |  |  | x | [5 empty] | x |  | Cost for presence
Co-simuate controlled MBM | 2 hours | [5 empty] | x |  |  | x
Check Dynamic Response | less than 1 hour |  |  | x | [5 empty] | x
Check Motor Power | less than 1 hour |  |  |  | x
Adapt Electrical Model | starts at 1 day... |  |  |  | x |  |  | x
Simulate Electrical Model | several hours | [6 empty] | x
Check Autonomy | less than 1 hour |  |  |  | x
Note on C1: Istvan, DAVID: It may be an interplay between the experts
Note on A7: Istvan, DAVID: Coupled work, lead by the mechanical engineer. (Much like in XP.)
Note on B8: Istvan, DAVID: we need some sort of an exponential coefficient here the CAM DSM tool may give an inspiration for this (side remark: DSM->PN)